## Sheet1
[SOUTHMANSFIELD INVENTORY SYSTEM] PROJECT SCHEDULE
PROJECT START DATE: AUGUST 23, 2016
|  | Aug 23 - 28 | Aug 29 - Sept 4 | Sept 5 -11 | Sept 12 - 18 | Sept 19 - 25 | Sept 26 - Oct 2 | Oct 3 - 9 | Oct 10 - 16 | Oct 17 - 23 | Oct 24 - 30 | Oct 31 - Nov 6 | Nov 7 - 13 | Nov 14 -20 | Nov 21 - 27 | Nov 28 - Dec 4 | Dec 5 - 11
WBS[ MANAGEMENT] | TASK | WEEK 0 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15s
1 | Develop Project Plan | bar: WEEK 0
1.1 | Update Project Plan | bar: WEEK 1
1.2 | Prepare Status Report | bar: WEEK 1
1.3 | Collect/ Analyze Project Metrics | bar: WEEK 1
1.4 | Conduct Reviews and Audits | bar: WEEK 0
1.5 | Prepare QA Plan | bar: WEEK 0
1.6 | Prepare CM Plan
1.7 | Develop Project Library
1.8 | Manage Change Board
1.9 | Maintain Configuration Items
[DESIGN]
2 | Develop Enterprise Architecture
2.1 | Prepare Data Flow Diagram | bar: WEEK 2
2.2 | Prepare Logical Data Model | bar: WEEK 2
2.3 | Prepare Physical Data Model | bar: WEEK 2
2.4 | Prepare Data Dictionary
2.5 | Develop Design Specification | bar: WEEK 2
2.6 | Review Design | bar: WEEK 2
[DEVELOPMENT]
3 | Develop Server Application | bar: WEEK 4
3.1 | Develop User Interface | bar: WEEK 4
3.2 | Develop XYZ Interface
3.3 | Procure Server | bar: WEEK 5
3.4 | ProcureWorkstation | bar: WEEK 6
3.5 | Procure Database | bar: WEEK 7
3.6 | Procure User Interface Building Tool | bar: WEEK 7
3.7 | Procure Opeating System | bar: WEEK 8
3.8 | Perform Integration Testing
3.9 | Develop Conversation Plan
3.1.1 | Develop User Manual
3.1.2 | Transition Management
[ACCEPTANCE TESTING]
4 | Plan Acceptance Test
4.1 | Conduct Acceptance Test
4.2 | Develop Test Report
[INSTALLATION]
5 | Develop Installation Plan
5.1 | Site Preparation
5.2 | Install at Location
[MAINTENANCE]
6 | Hardware Maintenance
6.1 | Software Maintenance